## Sheet1
Task Title | Task Description | Start Date | End Date | Duration | Status | Priority
Project Setup and Dependencies | Set up ASP.NET Core project with dependencies (Entity Framework, MySQL, etc.). Initialize and configure the project. | 2024-12-25 | 2024-12-25 | 1 hour | Completed | High
Models and DbContext Creation | Create models (Item, Receipt, ReceiptItem) and DbContext class with configuration for MySQL. | 2024-12-25 | 2024-12-25 | 2 hours | Completed | High
Database Migration and Verification | Add migration to create database tables and verify the database schema in MySQL. | 2024-12-25 | 2024-12-25 | 30 minutes | Completed | High
Create Controllers | Implemented the controllers to handle logic and user interactions for receipts and items. | 2024-12-26 | 2024-12-26 | 3 hours | Completed | High
Implement Stock Validation | Ensure that the system doesn't allow transactions for items with insufficient stock. | 2024-12-26 | 2024-12-26 | 1 hour | Completed | High
Deduct Balance After Sale | Update item balance and amounts sold after completing a transaction. | 2024-12-26 | 2024-12-26 | 1 hour | Completed | High
Test the System | Test all features, including adding receipts, stock validation, and balance deduction. | 2024-12-26 | 2024-12-26 | 1 hour | Completed | High
Final Adjustments | Make any necessary fixes and improvements based on testing. | 2024-12-26 | 2024-12-26 | 2 hours | Completed | Medium
Prepare Project Documentation | Prepare the ERD diagram and project documentation. | 2024-12-27 | 2024-12-27 | 2 hours | Completed | Medium